## Story
STORY BOARD
Requirement From | Task | Points | Priority | Status | Actual | Detail
Foundation | App framework | 4 | P1 | done
Foundation | SPIKE - Open Weather Map API | 6 | P1 | done
Foundation | MVP UI design | 4 | P1 | done
Hard | 1. Search by city name or zip code | 8 | P0 | done |  | Implement a search to allow the user to enter a city name or zip code. The result of the search is to display the current weather information for the searched location.
Hard | 2. Search by GPS | 4 | P0 | done |  | On the same search screen, also allow user to use GPS location instead to get current weather information.
Hard | 3. Most recent search location loads automatically | 8 | P0 | done |  | When you come back to the app after closing it, the weather for the most recent search is displayed.
Hard | 4. Recent Searches | 8 | P0 | done |  | Implement a screen that lists recently searched locations. You can tap on a recent search location and see the current weather location.
Hard | 5. Delete recent searches | 8 | P0 | done |  | Provide the ability to delete one or more recently searched locations.
| Weather Icon | 4 | P2 | done
| Styles and fonts | 4 | P2 | done
| MVP UI design v2 (more friendly UX, incl. landscape design) | 8 | P2 | excluded
| Refresh & loading spinner | 2 | P2 | done
| Error handling | 4 | P2 | done |  | empty recent list, empty current weather on both page
| Network status handling | 2 | P2 | excluded
| Splash screen | 2 | P2 | excluded
| Fuzzy search for city names/country code/Zip | 8 | P2 | 80%
| C/F temperture options | 4 | P2 | excluded
| Weather widget | 16 | P3 | excluded
| pre-packaged city database | 2 | P3 | excluded
| SUM | 92 |  |  | 0 | mins | 0 | hours